## ISD
INITIAL PLANNING
Week No | Task | Deliverable | Person assigned | Time | Is completed ? | Note
1 | Find and choose appropriate topic |  |  | 20/8/2017 - 2/9/2017 | Completed !
2 |  |  | All Members
3
FIRST ITERATION
4 | Initial planning (schedule) General, initial requirement. Define iteration First requirement | Related documents collection Requirement specifications (based on template): Stakeholder/ functional-non functional req… | Schedule: Hoàng Introduction: Chi Overall Description: Anh Function: Tiến Contract: Hà + Hoàng | 3/9/2017 - 10/9/2017 | Completed ! | Fixed some errors in template and contract
5 | Analysis & design | Analysis: Use case, Activity diagram / Usecase specs DB Design: Conceptual, logical, physical Code Design: Class diagram UI interface design WBS ( ID, Task, Person assigned, StartDate/EndDate, IsCompleted, Note) | Analysis: UC, Activity Diagram,Class Diagram - Tiến DB Design: Tiến / Anh / Chi UI Interface Design / Responsive: Hoàng | 10/9/2017 - 17/9/2017 | Completed !
6 | Implementation | Initial version | Front-end: Hoàng PHP: Tiến / Anh / Chi Tester: Hà | 17/9/2017 - 24/9/2017 | Not Completed !
Second Iteration
| Coding | ( Front-end include images, code css, htlm, js) |  | 24/9/2017 - 10/10/2017
7 |  | ( Back-end include code php, build database) | Psd Template and Coding Front-end: Hoàng |  | Completed ! | Check and fix error in coding
Post / Post Detail, All Clothes: Anh
8 |  |  | About us/ Manage Cart: Tiến
|  | Document ( user story, database specification) | Contact: Chi
9 |  |  | Tester: Hà | 10/10/2017 - 15/10/2017
Document : All member
10 | Testing | Receive Feedback from contact and fix product by their idea | User authentication, Review product : Chi
| Document |  | Manage Order, Checkout: Anh | 16/10/2017 - 25/10/2017
Register + Search/filter produc: Tiến
Reponsive Theme: Hoàng
Third Iteration
11 |  | ( Front-end include images, code css, htlm, js) | Manage employee / Manage order / Manage customer: Tiến | 26/10/2017 - 26/11/2017
12 | Coding | ( Back-end include code php, build database) | Manage admin account / Manage review / Manage post: Chi
13 |  |  | Manage about us / Manage contact /Manage product : Anh
14 | Testing |  | Dashboard UI / Responsive: Hoàng
15 |  |  | Tester: Hà |  | Completed !
|  |  | Document: All member | 27/11/2017 - 5/12/2017
16 | Document | Document( user story, install guide, software requirement need completed ) |  |  | Completed !
17 | Last fix
Give Product for contact and recive review