## Testplan
OVERVIEW
Purpose of the document: Test planning for the LALA STORE website Website description: This is a website that offers clothing online ordering services. Customers simply go to the website registered to become members of the website to choose the type of products to buy and order directly at the site without having to directly to the store. Customer requests are sent to the store, the store staff will contact the customer to confirm the order over the phone.
COSTS AND TESTING PLAN
Estimated 50 days of site testing
Estimated time is from October 25, 2017 to December 10, 2017
TEST STRATEGY Testing environment: Testing on the Desktop Browsers: - Cốc Cốc: 66.4.134 - Mozilla Firefox: 57.0.2 Test execution phase: System test Test type: - UI testing - Functional testing - Database testing Test method: Black Box Testing and Gray Box Testing CONDITIONAL ACCEPTANCE TO STOP TESTING >=80% of test cases are passed FUNCTIONS IN TESTING All the screens and functions of the website
REQUIRED DOCUMENTS - Test plan - Test design - Test cases - Test report
RISKS AND SOLUTIONS
| Risk | Solution | Performer
| Computer of tester was corrupt, disconnected | Borrowing the computer of the roommates/teammates | Ha
| Tester is sick | Overtime | Ha
| Server error, tester cannot access the database for testing | Report immediately to the server administrator to fix the problem | Ha

## Testing schedule
Progress Completed
Tast | Function |  | Performer | Intended start date | Intended end date | Estimated hours | Date of actual start | Actual end date | Actual hours | Level of completion
Writing testcase | HOMEPAGE | COMMON INTERFACE | Ha | 10/25/2017 | 12/10/2017 | 24h | 10/25/2017
|  | BANNER | Ha
|  | MENU | Ha
|  | FOOTER | Ha
|  | TOP PRODUCTS | Ha
|  | CLOTHING SCREEN | Ha
|  | NEWS SCREEN | Ha
|  | ABOUT SCREEN | Ha
| CONTACT US |  | Ha
| REGISTER |  | Ha
| LOGIN |  | Ha
| LOGOUT |  | Ha
| ORDERING |  | Ha
| CART |  | Ha
| SEARCHING PRODUCTS |  | Ha